## Goals
AAAI Conference timeline - VERIFY DATES ONE MONTH IN ADVANCE!! |  |  |  | https://aaai.org/Conferences/AAAI-20/aaai20call/
Year | Month | Date | Info
2020 | November | 10 | AAAI Acceptance/rejection notification
| October | 10 to 13 | Author feedback window
| September | 5 | Electronic papers due
| August | 30 | Electronic abstracts due
| 15 July to 30 August |  | Register on AAAI web site
| August |  | Write paper, start applying to conference
| to June |  | Analyze results, start applying to conference
| to mid Mar |  | Prong 3
| to mid Feb |  | Prong3
2020 | to mid Jan |  | Prong 2
| to mid Nov |  | Prong 2
| to mid Oct |  | Prong 1
| to mid Sep |  | Prong 1 - decision tree
| July, August |  | Get baseline working
2019 | July | 9 | Download papers
|  | 10 | Read one paper, look for code
|  | 11 | Read one paper, look for code
|  | 12 | Read three papers, look for code
|  | 13 | Read three papers
|  | 14 | Look for remaining code

## Document progress
2019 July | 4 to 8 | Google Machine Learning Crash Course
| 9 | Downloaded papers of task's teams who used at least one of the prongs
July-August |  | Reading papers, found baseline and NYU's code
August | 21 | Baseline code working, results comparable to what Duolingo published
| 31 | Trying to get NYU code working, installing the tools it uses, like Docker
September | 2 | NYU code: made progress towards getting the syntaxnet docker server running?